## Sheet1
Month | Milestone | Deliverable
1 | Project Initiation, Planning, and Feasibility Study | WBS, Gannt Chart, Network Diagram, Project Stakeholders and Objective report
2 | Research, Analysis, and System Architecture Design | System Architecture Report, Model Strategy Document
3 | Data Collection and Annotation | Data Collection Report
4 | Model Development (MVP) and Integration | MVP Model, Technical Integration Report, SRS, SDS
5 | Model Optimization and Enhancement | Hyperparameter Tuning Report
6 | Research Publication | Research Paper
7 | Cloud Deployment and Scalability Implementation | Deployment Report
8 | System Testing, Validation, and Final Documentation | Final Testing Report, Final Documentation